## Project Cover
Project Name | MCC Horizon Tower — Budgetary Estimate
Client | Megawide Construction Corporation
Location | Pasig City, Metro Manila
Building Type | Commercial Office
Contract Type | Lump Sum
Project Category | High-rise Building
CFA | 28500
Number of Buildings | 1
Number of Units | 42
Date | 2026-03-15
Revision | Rev B
Currency | PHP
Prepared By | J. Reyes, Senior Estimator

## Bid Summary Sheet
Direct Cost | 185000000
Indirect Cost | 18500000
Material Cost | 92000000
Labor Cost | 48000000
Equipment Cost | 15000000
Subcontract Cost | 30000000
Profit | 18500000
VAT | 26640000
Bid Price | 248640000
Grand Total | 248640000

## Cost Worksheet
Item No. | Description | Unit | Qty | Unit Rate | Amount
A | GENERAL REQUIREMENTS
A.1 | Temporary facilities and site offices | lot | 1 | 2500000 | 2500000
A.2 | Safety, HSE and PPE provisions | lot | 1 | 1800000 | 1800000
B | STRUCTURAL WORKS
B.1 | Structural concrete for columns and beams | m3 | 1200 | 12500 | 15000000
B.2 | Reinforcement bars grade 60 | kg | 450000 | 72 | 32400000
B.3 | Formworks and falseworks | m2 | 18000 | 850 | 15300000
C | ARCHITECTURAL WORKS
C.1 | Masonry CHB walls including plaster | m2 | 9500 | 1850 | 17575000
C.2 | Painting works for interior walls | m2 | 12000 | 420 | 5040000
D | ELECTRICAL WORKS
D.1 | Power distribution panelboards | lot | 1 | 8500000 | 8500000
D.2 | Lighting fixtures LED system | set | 2200 | 3200 | 7040000
E | MECHANICAL / HVAC
E.1 | VRV / VRF air-conditioning package | lot | 1 | 22000000 | 22000000
F | FIRE PROTECTION
F.1 | Automatic sprinkler system | lot | 1 | 9800000 | 9800000
G | PLUMBING AND SANITARY
G.1 | Cold and hot water piping system | lot | 1 | 6500000 | 6500000
H | EXTERNAL WORKS
H.1 | Site pavement and landscaping | lot | 1 | 4200000 | 4200000

## Resource Listing
Code | Description | Unit | Unit Cost | Category
MAT-C40 | Ready-mix concrete 4000 psi | m3 | 6800 | material
MAT-RB60 | Deformed rebar grade 60 | kg | 72 | material
LAB-MAS | Mason skilled | day | 950 | labor
EQP-MIX | Concrete mixer truck | day | 18000 | equipment
SUB-FP | Fire protection subcontract package | lot | 9800000 | subcontract

## Rate Analysis Detail
BOQ Item | Resource | Category | Unit | Consumption | Unit Cost | Productivity | Amount
B.1 | Ready-mix concrete 4000 psi | material | m3 | 1 | 6800 |  | 6800
B.2 | Deformed rebar grade 60 | material | kg | 1 | 72 |  | 72
C.1 | Mason skilled | labor | day | 0.15 | 950 | 6.5 | 142.5
F.1 | Fire protection subcontract package | subcontract | lot | 1 | 9800000 |  | 9800000

## Assumptions Notes
Assumptions
1. Rates are budgetary and exclude escalation beyond 90 days.
2. CFA based on architectural drawings Rev B.
Exclusions
1. Loose furniture and IT equipment.
2. Contaminated soil disposal beyond normal spoil.